PHASE 1 — FINALISATION CHECKLIST

Forgotten Felines Cat Rescue

| Compiled | 12 April 2026 | Charity No. | 1181190 |
| --- | --- | --- | --- |
| Owner | Sam Mathias | Purpose | Track all actions needed before trustee approval & publication |

Legend

| ADCH ADCH Minimum Welfare & Operational Standards | GDPR UK GDPR / ICO | CC Charity Commission (CC3 / governance duties) |
| --- | --- | --- |

A     Block A — Role Assignments

Must be resolved first — these are hard blockers. Policies with unresolved escalation paths cannot be published.

☐ Assign Lottery Licence Holder — must match the named individual on the active Gambling Act licence. Confirm with Bev who holds this.   ADCH   CC

☐ Assign Cat Intake Lead — needed for the intake procedure (ADCH Standards 1–4).   ADCH

☐ Assign Isolation Coordinator — can be the Vet Liaison (Becca James); just needs to be formally documented.   ADCH

☐ Assign Behavioural Support Contact — can be an external behaviourist; name and contact details needed (ADCH Standard 55).   ADCH

B     Block B — Missing Policies

Must be drafted before trustee approval — these policies do not yet exist as drafts.

☐ Consolidated Cats in Care Policy — combine cat-intake, cat-isolation-arrival, and fostering into a single ADCH-aligned policy. Individual drafts can remain as supporting documents.   ADCH

☐ Safeguarding Policy — must include statutory escalation steps (referral to police/social services). Required by Charity Commission and ADCH Standard 78.   ADCH   CC

☐ Incident Reporting & Complaints Policy — covers both internal complaints and Serious Incident Reporting to the Charity Commission.   CC

C     Block C — Trustee Approval of Existing Drafts

Drafts exist but must go through trustee sign-off before publication.

☐ Roles & Responsibilities Register — present for review and resolve remaining TBC entries   ADCH   CC

☐ Trustee Code of Conduct & Governance Policy   CC

☐ Financial Policy   CC

☐ Bullying Policy   CC

☐ Harassment Policy   CC

☐ GDPR Trustee Policy   GDPR   CC

☐ GDPR Volunteer Policy   GDPR

☐ Data Retention Policy   GDPR

☐ Privacy Notice — approve text before publishing to website   GDPR

☐ Record of Processing Activities (ROPA)   GDPR

☐ Data Breach Response Procedure   GDPR

☐ All ADCH animal care policies (intake, isolation, fostering, adoption, relinquishment, cleaning, transportation, escape, death, euthanasia)   ADCH

D     Block D — Publish and Distribute

Actions once trustee approval is complete.

☐ Publish Privacy Notice on the website — must be live before any public data collection continues.   GDPR

☐ Circulate Roles & Responsibilities Register to all trustees and foster coordinators.   ADCH   CC

☐ Issue published .docx copies of all approved policies.   ADCH   CC   GDPR

☐ Obtain signed acknowledgements from all trustees (Trustee Code of Conduct, GDPR Trustee Policy).   CC   GDPR

☐ Obtain signed acknowledgements from all active fosterers (Fostering Policy, GDPR Volunteer Policy, Volunteer Policy).   ADCH   GDPR

E     Block E — Documentation and Evidence

Records needed to evidence compliance — not policies, but operational artefacts.

☐ Complete nominated vet details — fill in phone numbers and primary contact names in the Roles & Responsibilities Register Section 5.   ADCH

☐ Document isolation arrangement with vet — written confirmation that the nominated vet can take in an infectious cat if needed (ADCH Standard 13).   ADCH

☐ Per-cat record log — one record per cat: description, intake date, vet history, assessments, adopter details. A Google Sheet is sufficient (ADCH Standard 76).   ADCH

☐ Fosterer training records — individual log of who was trained, on which of the 8 mandatory topics, and when (ADCH Standard 48).   ADCH

☐ Foster home assessment records — one record per approved foster home confirming it was visited (ADCH Standard 60).   ADCH

☐ Conflicts of interest register — maintained by the Chair; annual declaration required.   CC

☐ Confirm ICO fee registration status — check whether an annual data protection fee is required and up to date.   GDPR

F     Block F — Fosterer Training Programme

Required by ADCH Standard 48. Must cover all 8 mandatory topics with individual records kept.

☐ Write or adopt a fosterer training programme covering all 8 mandatory topics:   ADCH

– Animal welfare and recognising poor welfare

– Animal handling

– Animal behaviour

– Cleanliness and hygiene

– Feeding and food preparation

– Disease control

– Recognising and responding to sick animals (first aid action)

– New legislation, disease information, and inherited conditions

☐ Set a schedule for annual review of training content.   ADCH

G     Block G — ADCH Application

Once Blocks A–F are substantially complete.

☐ Complete the ADCH self-assessment against all applicable standards (SOP1, Step 3).   ADCH

☐ Gather application materials: 2 references (existing ADCH members or professionals — your vet qualifies), organisational constitution, 2 years of financial accounts or bank statements.   ADCH

☐ Submit application — email [email protected] or use the online form.   ADCH

Critical Path

Block A (assign remaining roles)  →  Block B (draft missing policies)  →  Block C (trustee approval session)  →  Block D (publish + distribute)

Blocks E, F, and G can run in parallel with B and C but must be complete before the ADCH application (G) is submitted.