# Phase 1 Finalisation Checklist — Forgotten Felines Cat Rescue

Charity No.: 1181190 Compiled: 2026-04-12 Last Updated: 2026-04-14 (restructured after comprehensive ADCH compliance rewrite) Owner: Sam Mathias Purpose: Consolidated list of everything needed before the Phase 1 policy suite can be trustee-approved and published.

Items are grouped by theme and sequenced so that blockers appear first. Each item is tagged with the compliance area(s) it serves.

________________________________________

## Legend

| Tag | Area |
| --- | --- |
| ADCH | ADCH Minimum Welfare & Operational Standards |
| GDPR | UK GDPR / ICO |
| CC | Charity Commission (CC3 / governance duties) |

________________________________________

## Block A — Role Assignments (Must be resolved first)

These are hard blockers. Policies with unresolved escalation paths cannot be published.

[ ] Assign Lottery Licence Holder — must match the named individual on the active Gambling Act licence. Confirm with Bev who holds this. ADCH CC

[ ] Assign Cat Intake Lead — needed for ADCH Standards 1–4 intake procedure and referenced in Cat Relinquishment Policy § 5. ADCH

[ ] Assign Behavioural Support Contact — internal or external behaviourist; name, contact details, and the scope of consultation (ADCH Standard 55, Fostering Policy § 3, Fosterer Training Programme Topic 3). ADCH

[x] Assign Isolation Coordinator — assigned to Becca James (Vet Liaison) in the Roles and Responsibilities Register v0.9. ADCH

________________________________________

## Block B — Missing Policies and Supporting Documents

Documents that are required and did not exist before the 2026-04-14 compliance sweep. All new animal-care documents have been drafted — they still need trustee sign-off in Block C.

[x] Fostering Policy v2.0 — closes Standards 47, 48, 59, 60, 62. ADCH

[x] Cat Intake and Medical Care Policy v2.0 — closes Standards 1–4, 51, 76 intake procedure. ADCH

[x] Cat Transportation Policy v2.0 — closes Standard 54 (group transport, view protection, long journeys). ADCH

[x] Adoption Policy v2.0 — closes Standards 71–75 (proof of address, care advice pack, supervised meetings, return welcome). ADCH

[x] Cat Isolation on Arrival Policy v2.0 — 72-hour vet window, Standard 12 documented procedure statement, Standard 13 isolation practice reference, Standards 49/50 feral handling. ADCH

[x] Cat Fosterer Cleaning Policy v2.0 — welfare-balance clause, chemical secure storage, change-of-occupancy dry-time. ADCH

[x] Cat Rescue Euthanasia Policy v2.0 — Standard 67 full examination, feral exception, fosterer consultation, Standard 69 IV preference. ADCH

[x] Cat Relinquishment Policy v2.0 — Standards 49–50 feral handling procedure. ADCH

[x] Death of a Cat Policy v2.0 — post-mortem decision chain, cremation detail, record update chain. ADCH

[x] Escape of a Cat Policy v2.0 — emergency authority matrix, recording template, review process. ADCH

[x] Social Media Policy v2.0 — Standard 79 cat welfare section, 2020 review date refreshed. ADCH

[x] Forgotten Felines Emergency Plan — Standards 46 and 78 emergency procedure covering fire, flood, power loss, illness, escape, death, human emergency. ADCH

[x] Foster Home Assessment Checklist — Standard 60 assessment artefact. ADCH

[x] Foster Home Register — Standard 60 log of approved homes. ADCH

[x] Named Veterinary Practices Register — Standards 13, 51 nominated practices and isolation provider. ADCH

[x] Per-Cat Record Specification — Standard 76 schema for the Current Cats system. ADCH

[x] Fosterer Training Programme — Standard 48 written programme covering the 8 mandatory topics. ADCH

[x] Vet Arrangement Letter Template — supports populating the Named Veterinary Practices Register. ADCH

### Still outstanding as new drafts

[ ] Safeguarding Policy — must include statutory escalation steps (referral to police/social services). Required by Charity Commission and ADCH Standard 78. ADCH CC

[ ] Incident Reporting & Complaints Policy — covers both internal complaints and Serious Incident Reporting to the Charity Commission. CC

[ ] Fostering Agreement template — signed by every fosterer before first placement (referenced in the Fostering Policy § 2 and Foster Home Assessment Checklist). ADCH

________________________________________

## Block C — Trustee Approval of Existing Drafts

These documents exist as drafts but must go through trustee sign-off before publication. All v2.0 animal-care policies are new drafts and need approval.

[ ] Roles & Responsibilities Register v0.9 — present for review and resolve remaining TBC entries ADCH CC

[ ] Trustee Code of Conduct & Governance Policy CC

[ ] Financial Policy CC

[ ] Bullying Policy CC

[ ] Harassment Policy CC

[ ] GDPR Trustee Policy GDPR CC

[ ] GDPR Volunteer Policy GDPR

[ ] Data Retention Policy GDPR

[ ] Privacy Notice — approve text before publishing to website GDPR

[ ] Record of Processing Activities (ROPA) GDPR

[ ] Data Breach Response Procedure GDPR

[ ] All v2.0 ADCH animal-care policies (intake, isolation, fostering, adoption, relinquishment, cleaning, transportation, escape, death, euthanasia) ADCH

[ ] Forgotten Felines Emergency Plan ADCH

[ ] Foster Home Assessment Checklist ADCH

[ ] Foster Home Register ADCH

[ ] Named Veterinary Practices Register ADCH

[ ] Per-Cat Record Specification ADCH GDPR

[ ] Fosterer Training Programme ADCH

[ ] Social Media Policy v2.0 ADCH GDPR

________________________________________

## Block D — Publish and Distribute

Actions once trustee approval is complete.

[ ] Publish Privacy Notice on the website — must be live before any public data collection continues. GDPR

[ ] Circulate Roles & Responsibilities Register to all trustees and foster coordinators. ADCH CC

[ ] Circulate Emergency Plan and Emergency Quick Reference Card to every active fosterer. ADCH

[ ] Issue published `.docx` copies of all approved policies. ADCH CC GDPR

[ ] Obtain signed acknowledgements from all trustees (Trustee Code of Conduct, GDPR Trustee Policy). CC GDPR

[ ] Obtain signed acknowledgements from all active fosterers (Fostering Policy, GDPR Volunteer Policy, Volunteer Policy, Emergency Plan). ADCH GDPR

________________________________________

## Block E — Populate Operational Systems

Records and live systems needed to evidence compliance — the structures exist, the data must be filled in.

[ ] Populate the Named Veterinary Practices Register — send the Vet Arrangement Letter Template to each practice; record phone, contact, and arrangement letter status. ADCH (Std 51)

[ ] Designate a Standard 13 isolation practice — one nominated practice confirmed in writing as the isolation provider. ADCH (Std 13)

[ ] Build the Current Cats per-cat record system — Google Sheet or equivalent, matching the Per-Cat Record Specification schema. Populate with all current cats. ADCH (Std 76)

[ ] Build the Foster Home Register live entries — one row per currently active foster home, fully populated against the schema. ADCH (Std 60)

[ ] Run the Foster Home Assessment Checklist for every active foster home — capture Annex B measurements, approve, file checklist, update Foster Home Register. ADCH (Std 60)

[ ] Fosterer Training Record — open one record per active fosterer; mark training status for each of the 8 mandatory topics. Schedule induction or refresher for any fosterer not yet signed off on all topics. ADCH (Std 48)

[ ] Conflicts of interest register — maintained by the Chair; annual declaration required. CC

[ ] Confirm ICO fee registration status — check whether an annual data protection fee is required and up to date. GDPR

________________________________________

## Block F — Deliver Fosterer Training

Required by ADCH Standard 48.

[x] Write the Fosterer Training Programme covering all 8 mandatory topics. ADCH

[ ] Deliver induction training to every active fosterer using the programme. ADCH

[ ] Record sign-off for each topic per fosterer in the Fosterer Training Record. ADCH

[ ] Schedule annual refresher for each fosterer; set review reminders. ADCH

[ ] Annual programme review — Fostering Coordinator + Trustee sign-off. ADCH

________________________________________

## Block G — ADCH Application

Once Blocks A–F are substantially complete.

[ ] Complete the ADCH self-assessment using the comprehensive standards map in the ADCH Compliance Analysis (SOP1, Step 3). ADCH

[ ] Gather application materials:

- 2 references (existing ADCH members or professionals — your vet qualifies)   - Organisational constitution   - 2 years of financial accounts or bank statements

[ ] Submit application — email [email protected] or use the online form. ADCH

________________________________________

## Summary: Critical Path

The minimum viable path to trustee approval and publication is:

Block A (assign remaining roles)
  → Block B (draft missing policies: Safeguarding, Incident Reporting, Fostering Agreement)
    → Block C (trustee approval session — full animal-care v2.0 suite + registers + Emergency Plan)
      → Block D (publish + distribute)
        → Block E + F (populate systems, deliver training — can run in parallel)
          → Block G (ADCH application)

Block E can start in parallel with Block C, since populating registers does not require final trustee sign-off of the underlying policy (only the policy structure).

________________________________________

## Detailed Checklists by Area

For the full itemised breakdown by compliance framework, see:

ADCH Compliance Analysis — full standards map

ADCH Policy Suite Audit 2026-04-14

ADCH Compliance Checklist

GDPR Compliance Checklist

Charity Commission Compliance Checklist